## v1.4
Name / Description | Priority | Size estimate (Points) | State | Target iteration | Assig-ned To | Effort estimate left (hours) | Hours worked | Reference material
Produce Vision Document | 1 | 3 | Closed | 1.1 | Annie, Betül, Elif, Özde | 0 | 6 | <Samwise_VisionDocument.doc>
Produce Glossary | 1 | 2 | Closed | 1.1 | Betül | 0 | 4 | <Samwise_Glossary.doc>
Create System-Wide Requirements Specification Document | 3 | 3 | Closed | 1.1 | Annie | 0 | 6 | <Samwise_SystemWideReqSpec.doc>
Design Use Case Models | 3 | 3 | Closed | 1.1 | Özde | 0 | 6 | <Samwise_UCSpecification.doc>
Create Project Plan Document | 2 | 3 | Closed | 1.1 | Elif | 0 | 6 | <Samwise_ProjectPlan.doc>
Create Iteration Plan 1 Document | 2 | 5 | Closed | 1.1 | Betül | 0 | 10 | <Samwise_IterationPlan_1.doc>
Create Work Items List | 2 | 3 | Closed | 1.1 | Özde | 0 | 6 | <Samwise_WorkItemsList.xls>
Create Risk List | 3 | 3 | Closed | 1.1 | Annie | 0 | 6 | <Samwise_RiskList.xls>
Plan Second Iteration | 2 | 8 | Closed | 1.1 | Elif | 0 | 16
Create Iteration Plan 2 Document | 2 | 5 | Closed | 1.1 | Betül | 0 | 10 | <Samwise_IterationPlan_2.doc>
Technical Research for Implementation | 1 | 8 | Closed | 1.2 | Annie, Özde | 0 | 16
Backend Framework Research | [5 empty] | 0 | 6
Frontend Framework Research | [5 empty] | 0 | 6
Database Research | [5 empty] | 0 | 6
Design User Interface | 2 | 8 | Closed | 1.2 | Elif | 0 | 16
Design Database | 2 | 5 | Closed | 1.2 | Annie | 0 | 10
Create Architectural Notebook Document | 2 | 5 | Closed | 1.2 | Elif | 0 | 10 | <Samwise_ArchitectureNotebook.doc>
Revise the Documents Created at Iteration 1 | 3 | 5 | Closed | 1.2 | Annie | 0 | 10
Start Implementation and Testing of Use Case 5: Manage User Account | 1 | 13 | Closed | 1.2 | Özde | 0 | 26 | <UC: Manage User Account>
Implement Backend Features | [5 empty] | 0 | 6
Implement Frontend Features | [5 empty] | 0 | 5
Unit Test of Implemented Features | [5 empty] | 0 | 5
UI/UX Test of Implemented Features | [5 empty] | 0 | 5
User Acceptance Test of Implemented Features | [5 empty] | 0 | 5
Start Implementation and Testing of Use Case 9: Manage Service | 2 | 13 | Closed | 1.2 | Annie,Elif | 0 | 26 | <UC: Manage Service>
Implement Backend Features | [5 empty] | 0 | 6
Implement Frontend Features | [5 empty] | 0 | 5
Unit Test of Implemented Features | [5 empty] | 0 | 5
UI/UX Test of Implemented Features | [5 empty] | 0 | 5
User Acceptance Test of Implemented Features | [5 empty] | 0 | 5
Plan Third Iteration | 3 | 3 | Closed | 1.2 | Annie, Elif, Özde | 0 | 6
Create Iteration Plan 3 Document | 3 | 3 | Closed | 1.2 | Annie, Elif, Özde | 0 | 6 | <Samwise_IterationPlan_3.doc>
Design User Interface | 1 | 8 | Closed | 1.3 | Annie | 0 | 16
Design Database | 1 | 5 | Closed | 1.3 | Özde | 0 | 10
Revise the Documents Created at Iteration 2 | 2 | 5 | Closed | 1.3 | Annie, Özde | 0 | 10
Start Implementation and Testing of Use Case 2: Search Service | 1 | 13 | Closed | 1.3 | Elif | 0 | 26 | <UC: Search Service>
Implement Backend Features | [5 empty] | 0 | 6
Implement Frontend Features | [5 empty] | 0 | 5
Unit Test of Implemented Features | [5 empty] | 0 | 5
UI/UX Test of Implemented Features | [5 empty] | 0 | 5
User Acceptance Test of Implemented Features | [5 empty] | 0 | 5
Plan Fourth Iteration | 3 | 3 | Closed | 1.3 | Elif, Annie | 0 | 6
Create Iteration Plan 4 Document | 3 | 3 | Closed | 1.3 | Elif, Özde | 0 | 6
Design User Interface | 1 | 8 | Open | 1.4 | Annie | 16 | 0
Design Database | 1 | 5 | Open | 1.4 | Özde | 10 | 0
Revise the Documents Created at Iteration 3 | 2 | 5 | Open | 1.4 | Annie, Özde | 10 | 0
Start Implementation and Testing of Use Case 1: Schedule Appointment | 1 | 13 | Open | 1.4 | Elif, Annie Özde | 26 | 0 | <UC: Schedule Appointment>
Implement Backend Features | [5 empty] | 6 | 0
Implement Frontend Features | [5 empty] | 5 | 0
Unit Test of Implemented Features | [5 empty] | 5 | 0
UI/UX Test of Implemented Features | [5 empty] | 5 | 0
User Acceptance Test of Implemented Features | [5 empty] | 5 | 0
Start Implementation and Testing of Use Case 12: Approve Appointment | 1 | 13 | Open | 1.4 | Elif, Annie Özde | 26 | 0 | <UC: Approve Appointment>
Implement Backend Features | [5 empty] | 6 | 0
Implement Frontend Features | [5 empty] | 5 | 0
Unit Test of Implemented Features | [5 empty] | 5 | 0
UI/UX Test of Implemented Features | [5 empty] | 5 | 0
User Acceptance Test of Implemented Features | [5 empty] | 5 | 0
Release 1 -Demo | 1 | 8 | Open | 1.4 | Elif | 16 | 0
Deploy Software on Production Environment | 1 | 5 | New | 1.5
Configure Software for Hardware | 1 | 3 | New | 1.5
Start Implementation and Testing of Use Case 4: Manage Proposal | 1 | 13 | New | 2.1
Start Implementation and Testing of Use Case 6: Ask Help | 1 | 13 | New | 2.1
Start Implementation and Testing of Use Case 8: Make Proposal for Discount | 1 | 13 | New | 2.2
Start Implementation and Testing of Use Case 10: Receive Payment | 1 | 13 | New | 2.2
Start Implementation and Testing of Use Case 3: Make Payment | 1 | 13 | New | 2.3
Start Implementation and Testing of Use Case 11: Troubleshoot System | 1 | 13 | New | 2.3
Start Implementation and Testing of Use Case 7: Write Review | 1 | 13 | New | 2.4
Release 2 -Demo | 1 | 8 | New | 2.4

## Revision Table
Version | Description | Date | Person
1 | The document was created. | 04.11.2023 | Özde Uysal
1.1 | The document was revised according to Iteration 1 feedback. | 11.11.2023 | Özde Uysal
1.2 | The document was updated for Iteration 2. | 25.11.2023 | Özde Uysal
1.3 | The document was revised according to Iteration 2 feedback and to accomodate the loss of resource. | 02.12.2023 | Özde Uysal
1.4 | The document was updated for Iteration 3. | 16.02.2023 | Özde Uysal Annie Yang