## SamwiseRiskList_v1.3
Risk ID | Date Identified | Headline | Description | Type | Impact | Probability | Magnitude | Owner | Mitigation Strategy
1 | 04.11.2023 | Inadequate allocation of resources | Inadequate allocation of resources, including personnel and budget, may lead to migration delays or issues. | Resource | 5 | 50% | 2.5 | Annie Yang | Allocate sufficient resources, including skilled personnel and budget, to ensure a smooth migration process.
2 | 04.11.2023 | Service Provider Disputes | Frequent disputes and conflicts between service providers and users. | Business | 3 | 70% | 2.1 | Özde Uysal | Implement a mediation process, clarify service terms, and improve communication channels.
3 | 04.11.2023 | Data Breach | Unauthorized access to user data due to a security vulnerability or breach. | Technical | 5 | 40% | 2 | Özde Uysal | Regular security audits, encryption, and strict access controls.
4 | 04.11.2023 | App Performance Degradation | Deterioration in app performance as the user base and service listings grow. | Technical | 4 | 40% | 1.6 | Elif Beril Sayli | Regularly optimize code, implement scaling solutions, and conduct performance testing.
5 | 04.11.2023 | Service Provider Verification Delays | Slow verification of service providers, resulting in delays in service availability. | Resource | 3 | 50% | 1.5 | Elif Beril Sayli | Streamline the verification process, allocate additional resources.
6 | 04.11.2023 | Inadequate Testing | Inadequate testing of the new environment can lead to unforeseen issues. | Technical | 3 | 40% | 1.2 | Özde Uysal | Thoroughly test the new environment and migration process, including both functional and security testing with detail.
7 | 04.11.2023 | Legal Compliance Issues | Failure to comply with GDPR and Turkish KVKK regulations. | Compliance | 5 | 20% | 1 | Annie Yang | Regular legal compliance audits and training.
8 | 04.11.2023 | Data Backup and Recovery Risks | Data backup and recovery processes may fail, leading to data loss. | Technical | 3 | 30% | 0.9 | Elif Beril Sayli | Ensure that robust backup and recovery procedures are in place, and regularly test data recovery mechanisms.
9 | 25.11.2023 | Loss of Team Member | Unexpected departure of a team member, impacting project timelines and knowledge base. | Resource | 4 | 20% | 0.8 | Annie Yang | Cross-train team members, maintain documentation, and have a contingency plan for workload redistribution.
10 | 04.11.2023 | Authentication vulnerabilities | Authentication vulnerabilities can cause the security leaks. | Technical | 2 | 30% | 0.6 | Özde Uysal | Strong password policies, multi-factor authentication can prevent vulnerabilities.
11 | 04.11.2023 | Payment Platform Issues | Incompatibility or issues with third-party payment platforms. | Technical | 4 | 10% | 0.4 | Elif Beril Sayli | Regularly update payment platform integrations.
12 | [6 empty] | 0
13 | [6 empty] | 0
14 | [6 empty] | 0
15 | [6 empty] | 0
16 | [6 empty] | 0
17 | [6 empty] | 0
18 | [6 empty] | 0

## Revision Table
Version | Description | Date | Person
1 | The document was created. | 04.11.2023 | Elif Beril Sayli Özde Uysal Annie Yang
1.1 | The document was revised according to Iteration 1 feedback. | 11.11.2023 | Elif Beril Sayli Özde Uysal Annie Yang
1.2 | The document was updated for Iteration 2. | 25.11.2023 | Elif Beril Sayli Özde Uysal Annie Yang
1.3 | The document was revised according to Iteration 2 feedback for stakeholders. | 02.12.2023 | Annie Yang