## v1.1
Name / Description | Priority | Size estimate (Points) | State | Target iteration | Assig-ned To | Effort estimate left (hours) | Hours worked | Reference material
Produce Vision Document | 1 | 3 | Closed | 1.1 | Annie, Betül, Elif, Özde | 0 | 6 | <Samwise_VisionDocument.doc>
Produce Glossary | 1 | 2 | Closed | 1.1 | Betül | 0 | 4 | <Samwise_Glossary.doc>
Create System-Wide Requirements Specification Document | 3 | 3 | Closed | 1.1 | Annie | 0 | 6 | <Samwise_SystemWideReqSpec.doc>
Design Use Case Models | 3 | 3 | Closed | 1.1 | Özde | 0 | 6 | <Samwise_UCSpecification.doc>
Create Project Plan Document | 2 | 3 | Closed | 1.1 | Elif | 0 | 6 | <Samwise_ProjectPlan.doc>
Create Iteration Plan 1 Document | 2 | 5 | Closed | 1.1 | Betül | 0 | 10 | <Samwise_IterationPlan_1.doc>
Create Work Items List | 2 | 3 | Closed | 1.1 | Özde | 0 | 6 | <Samwise_WorkItemsList.xls>
Create Risk List | 3 | 3 | Closed | 1.1 | Annie | 0 | 6 | <Samwise_RiskList.xls>
Plan Second Iteration | 2 | 8 | Closed | 1.1 | Elif | 0 | 16
Create Iteration Plan 2 Document | 2 | 5 | Closed | 1.1 | Betül | 0 | 10 | <Samwise_IterationPlan_2.doc>
Technical Research for Implementation | 1 | 8 | Open | 1.2 | Annie, Özde | 16 | 0
Backend Framework Research | [5 empty] | 6 | 0
Frontend Framework Research | [5 empty] | 6 | 0
Database Research | [5 empty] | 6 | 0
Design User Interface | 2 | 8 | Open | 1.2 | Elif | 16 | 0
Design Database | 2 | 5 | Open | 1.2 | Annie | 10 | 0
Create Architectural Notebook Document | 2 | 5 | Open | 1.2 | Elif | 10 | 0
Design Data, Deployment, Domain Models | 2 | 5 | Open | 1.2 | Özde | 10 | 0
Revise the Documents Created at Iteration 1 | 3 | 5 | Open | 1.2 | Annie | 10 | 0
Start Implementation and Testing of Use Case: Manage User Account | 1 | 13 | Open | 1.2 | Betül, Özde | 26 | 0 | <UC: Manage User Account>
Implement Backend Features | [5 empty] | 6 | 0
Implement Frontend Features | [5 empty] | 5 | 0
Unit Test of Implemented Features | [5 empty] | 5 | 0
UI/UX Test of Implemented Features | [5 empty] | 5 | 0
User Acceptance Test of Implemented Features | [5 empty] | 5 | 0
Start Implementation and Testing of Use Case: Manage Service | 2 | 13 | Open | 1.2 | Annie,Elif | 26 | 0 | <UC: Manage Service>
Implement Backend Features | [5 empty] | 6 | 0
Implement Frontend Features | [5 empty] | 5 | 0
Unit Test of Implemented Features | [5 empty] | 5 | 0
UI/UX Test of Implemented Features | [5 empty] | 5 | 0
User Acceptance Test of Implemented Features | [5 empty] | 5 | 0
Plan Third Iteration | 3 | 3 | Open | 1.2 |  | 6 | 0
Create Iteration Plan 3 Document | 3 | 3 | Open | 1.2 |  | 6 | 0
Start Implementation and Testing of Use Case: Search Service | 1 | 13 | New | 1.3 |  | 26 | 0 | <UC: Search Service>
Implement Backend Features | [5 empty] | 6 | 0
Implement Frontend Features | [5 empty] | 5 | 0
Unit Test of Implemented Features | [5 empty] | 5 | 0
UI/UX Test of Implemented Features | [5 empty] | 5 | 0
User Acceptance Test of Implemented Features | [5 empty] | 5 | 0
Start Implementation and Testing of Use Case: Schedule Appointment | 2 | 13 | New | 1.3 |  | 26 | 0 | <UC: Schedule Appointment>
Implement Backend Features | [5 empty] | 6 | 0
Implement Frontend Features | [5 empty] | 5 | 0
Unit Test of Implemented Features | [5 empty] | 5 | 0
UI/UX Test of Implemented Features | [5 empty] | 5 | 0
User Acceptance Test of Implemented Features | [5 empty] | 5 | 0
Plan Fourth Iteration | 3 | 3 | New | 1.3 |  | 6 | 0
Create Iteration Plan 4 Document | 3 | 3 | New | 1.3 |  | 6 | 0
Start Implementation and Testing of Use Case: Manage Timetable | 1 | 13 | New | 1.4 |  | 26 | 0 | <UC: Manage Timetable>
Implement Backend Features | [5 empty] | 6 | 0
Implement Frontend Features | [5 empty] | 5 | 0
Unit Test of Implemented Features | [5 empty] | 5 | 0
UI/UX Test of Implemented Features | [5 empty] | 5 | 0
User Acceptance Test of Implemented Features | [5 empty] | 5 | 0
Start Implementation and Testing of Use Case: Ask Help | 2 | 13 | New | 1.4 |  | 26 | 0 | <UC: Ask Help>
Implement Backend Features | [5 empty] | 6 | 0
Implement Frontend Features | [5 empty] | 5 | 0
Unit Test of Implemented Features | [5 empty] | 5 | 0
UI/UX Test of Implemented Features | [5 empty] | 5 | 0
User Acceptance Test of Implemented Features | [5 empty] | 5 | 0
Release 1 -Demo | 1 | 8 | New | 1.4 |  | 16 | 0
Start Implementation and Testing of Use Case: Make Proposal for Discount | 1 | 32 | New | 2.1
Start Implementation and Testing of Use Case: Receive Payment | 1 | 34 | New | 2.2
Start Implementation and Testing of Use Case: Make Payment | 1 | 20 | New | 2.3
Start Implementation and Testing of Use Case: Write Review | 1 | 32 | New | 2.4
Release 2 -Demo | 1 | 8 | New | 2.4