## Sheet1
Name / Description | Priority | Size estimate (Points) | State | Target iteration | Assig-ned To | Effort estimate left (hours) | Hours worked | Reference material
Produce draft vision | 1 | 3 | Closed | 1 | Annie, Betül, Elif, Özde | 0 | 6
Produce glossary | 1 | 2 | Closed | 1 | Betül | 0 | 4
Create System-Wide Requirements Specification document | 3 | 3 | Open | 1 | Annie | 0 | 6 | <systemwide_req_spec.doc>
Design Use Case Model | 3 | 3 | Open | 1 | Özde | 0 | 6 | <uc_specification.doc>
Create Project Plan document | 2 | 3 | Open | 1 | Elif | 0 | 6 | <project_plan.doc>
Create Iteration Plan document | 2 | 5 | Open | 1 | Betül | 0 | 10 | <iteration_plan.doc>
Create Work Items list | 2 | 3 | Open | 1 | Özde | 0 | 6 | <work_items_list.xls>
Create Risk list | 3 | 3 | Open | 1 | Annie | 0 | 6 | <risk_list.xls>
Create end user documentation | 2 | 8 | Open | 1 | Elif | 16 | 0
Support creating user account process | 2 | 21 | New | 2 | Betül | 42 | 0 | <UC: Create User Account>
Prototype UI |  |  | New |  |  | 6 | 0
Do the design |  |  | New |  |  | 8 | 0
Implement and test creating user account process |  |  | New |  |  | 22 | 0
Update end user documentation |  |  | New |  |  | 6 | 0
Complete creating user account process | 2 | 8 | New | 2 |  | 16 | 0
Support basic managing services process | 1 | 55 | New | 2 | Özde | 70 | 0 | <UC: Manage Services>
Prototype UI |  |  | New |  | Betül | 6 | 0
Do the design |  |  | New |  | Annie | 14 | 0
Implement and test managing services process |  |  | New |  | Elif | 50 | 0
Support basic creating appointments process | 1 | 55 | New | 3 |  | 90 | 0 | <UC: Schedule Appointment>
Prototype UI |  |  | New |  |  | 6 | 0
Do the design |  |  | New |  |  | 8 | 0
Implement scheduling reservations function |  |  | New |  |  | 20 | 0
Implement and test creating appointments process |  |  | New |  |  | 50 | 0
Update end user documentation |  |  | New |  |  | 6 | 0
Complete the managing services/reservations process | 2 | 8 | New | 3 |  | 16 | 0
Add authentication during user login | 3 | 13 | New | 4 |  | 26 | 0
Support chatbot service | 4 | 21 | New | 4 |  | 42 | 0 | <UC: Chat Support service>
Prototype UI |  |  | New |  |  | 8 | 0
Do the design |  |  | New |  |  | 10 | 0
Implement and test chatbot service |  |  | New |  |  | 20 | 0
Update end user documentation |  |  | New |  |  | 4 | 0
Complete chatbot service | 5 | 8 | New | 4 |  | 16 | 0
Support filtering services process | 3 | 34 | New | 4 |  | 60 | 0 | <UC: Filter Options for User Searches>
Prototype UI |  |  | New |  |  | 8 | 0
Do the design |  |  | New |  |  | 12 | 0
Implement and test filtering function |  |  | New |  |  | 35 | 0
Update end user documentation |  |  | New |  |  | 5 | 0
Complete filtering process | 3 | 8 | New | 4 |  | 16 | 0
Edit end user documentation | 2 | 8 | New | 4 |  | 16 | 0